## Sheet1
Project Management Software Tools In-Class Exercise with Gantter 1. Enter the Tasks noted below in a logical order in Gantter. 2. Enter and Indent the Tasks that are Sub-Tasks in a logical order within the broader Task 3. Enter the Task Duration for each Task or Sub-Task as noted below. 4. Enter the Resources and Cost for each Resource as noted below. 5. Establish the Predecessors and Link Tasks and Sub-Tasks as appropriate using Agile for Design, Construction, and Testing. 6. Estimate the Total Duration of the Project. 7. Estimate the Human Resource Costs detailed in this Project Plan. 8. For extra credit, investigate if you can reduce the total Project duration by adding Resources and what the Cost Impact would be.
Tasks and Sub-Tasks | Duration | Resources | Predecessors
Implementation | 30 days | CE 1, 2, 3 | Testing Complete
Milestone - Design Complete | 0 days |  | Design Integration of Frontend and Backend
Analyze Test Results | 2 days
Construction - Install Hardware | 30 days |  | Construction - Delivery Hardware
Test Plan | 2 days | CE 1, SE 1 | Design Complete
Develop Charter & Plan |  |  | Initialize Project Complete
Milestone - Construction Complete | 0 days
Design - Hardware | 5 days | CE 1, CE 2 | Analysis Complete
Analysis - CBA | 3 days | BA 1, BA 2 | Develop Charter and Plan
Construction - Plan | 10 days | CE 1, 2 | Design Complete
Close Project | 5 days | PM, TA 1, BA 1 | Implementation Complete
Construction - Delivery Hardware | 60 days | CE 10% | Construction - Order Hardware
Construction - Order Software | 5 days | SE 1, 2 | Design Complete
Milestone - Testing complete | 0 days
Testing
Construction - Software Delivery | 30 days | SE 10% | Construction - Software Order
Design
Carry out Test Plan | 5 days | QE 1, 2, SE 1, CE 1 | Test Plan Complete
Analysis - Technology | 3 days | TA 1, 2 | Develop Charter and Plan
Construction
Construction - Order Hardware | 5 days | CE 1, 2 | Design Complete
Initialize Project | 5 days | PM, TA 1, BA 1 | Project aligned with MOV and Strategy
Analysis
Develop Plan | 10 days | PM, TA1, BA 1 | Initialize Project
Evaluate Project Success | 5 days | PM, TA 1, BA 1 | Close Project
Design Requirements | 5 days | CE 1, SE 1, TA 1, BA 1 | Analysis Complete
Develop Charter | 5 days | PM, TA 1, BA 1 | Initialize Project Complete
Design Database | 4 days | SE 1, SE 2 | Analysis Complete
Analysis - Make/Buy | 5 days | PM, BA 1, TA 1 | Develop Charter and Plan Complete
Test Results approved by client | 3 days | PM, CE 1, SE 1, QE 1 | Carry out test plan complete
Design User Interface | 15 days | SE 1, DES 1, DES 2 | Analysis Complete
Design Integration of Backend and Frontend | 10 days | SE 1, SE 2 | Design UI and Design HW Complete
Resources | Abbreviation | Cost of Resource
Project Manager | PM | $150,000/yr
Technical Analyst | TA | $100,000/yr
Business Analyst | BA | $90,000/yr
Software Engineer | SE | $120,000/yr
Computer and Systems Engineer | CE | $110,000/yr
Quality Engineer | QE | $100,000/yr
Designer | DES | $100,000/yr