## Slide 1: Gantter Project Primer
Managing IT Resources

## Slide 2: View Tab
“Check” the following items:
  Sidebar
  Info Column
  Duration Column
  Work Column
  Cost Column
  Start Column
  Predecessors Column
  Resources Column

## Slide 3: Project/Properties/General Tab
Create new project name
Set Calendar to 24-hour
Set Start date to 08/30/2012
Plan from Start date
Save

## Slide 4: Project/Properties/Duration Tab
Hours in a day - 24
Days in a week - 7
Days in a month - 30
Save

## Slide 5: Project/Properties/Time Defaults Tab
Default Start Time – 12:00 AM
Default Finish Time- 11:59 PM
Save

## Slide 6: Resources Category
Add Resource Names
  Individual team members (initials)
  Team
  Client contacts
Type is Work
Set Cost rate for each resource in $/hr

## Slide 7: Tasks Category
Create tasks
For each task, Set Task Properties/Advanced
  Type: Fixed duration, uncheck "Effort Driven”
Set task/sub-task hierarchy by indenting
Set estimated duration in days
Set dependencies between tasks - Predecessors
Set constraints, if any
Set Milestones as 0 duration

## Slide 8: Allocation
Allocate resources to task
Set estimated work hours in Work column
If desired, adjust hours/resource/task - using resource usage %