## Sheet1
Rick Management In-Class Exercise 1. Download the "Risk Analysis Excel Spreadsheet" from LMS 2. Using the "Risk Category", "Risk", "Probability of Problem", and "Impact" data below, complete "Weight of Risk", "Probability*Impact $$", and "Probability*Impact Score" Columns 3. Use the "Weight of Risk" values and the "Probability*Impact Score" data to populate the "Weight" and "Score" values for each type of Risk in the "Risk Analysis Spreadsheet" 4. Find the "Risk Index" and the associated "Discount Rate" for this scenario 5. Insert the "Discount Rate" from this scenario into your CBA In-Class Exercise Spreadsheet and determine the NPV for the Project 6. *Optional* Find the "Total Duration of your Gantter Project Plan In-Class Exercise and correct the "Implementation Timeline" "Probability*Impact Score. What does this do to the "Risk Index" and the "Discount Rate"? What does this do to the NPV of the CBA? 7. Insert the answer to question 5 into this spreadsheet in cell A16 and highlight in red. 8. Submit this "Risk Managment In-Class Exercise" Spreadsheet with a file name that begins with your last name and the Edited "Risk Analysis" Spreadsheet with a file name that begins with your last name on LMS.
Risk Category | Risk | Probability of Problem | Impact | Weight of Risk (% of all impacts) | Probability * Impact $$ | Probability*Impact Score Assuming 0-3 Range Rounded to Whole Number | 0 < x <= 0.33: 1; 0.34< x <= 0.66: 2; x > 0.67: 3
Technology | Level of Complexity | 50% | 200000 | 20% | 100000 | 0.88889 | 3
Technology | Level of Customization | 20% | 100000 | 10% | 20000 | 0.17778 | 1
Technology | Configuration Detail | 30% | 50000 | 5% | 15000 | 0.13333 | 1
Resource | Availability of Resource | 60% | 100000 | 10% | 60000 | 0.53333 | 2
Resource | Skill Level of Available Resources | 20% | 80000 | 8% | 16000 | 0.14222 | 1
Resource | Cost of Training Personnel | 90% | 20000 | 2% | 18000 | 0.16 | 1
Organizational Risk | Percentage of Business Units affected | 25% | 50000 | 5% | 12500 | 0.11111 | 1
Organizational Risk | Process Change Required | 30% | 200000 | 20% | 60000 | 0.53333 | 2
Implementation | Timeline | 30% | 50000 | 5% | 15000 | 0.13333 | 1
Implementation | Impact on Existing Systems | 75% | 150000 | 15% | 112500 | 1 | 3
Sum |  |  | 1000000 | 100% | 429000 | 3.8133
69970 | (Using the “Solution” from the in class slides. For some reason the numbers on the in class slide didn’t match up with the original values that we had to work with, but I changed my numbers to reflect the slides from this week.)